## Sheet1
Task Name | Assignee | Task Status | Expected time to finish | Actual time to finish
DIO | MAhmoud Sarhan | completed | 0.5 | 0.5
Timer | Hejazy
ADC | Arafa
Keypad | Basel
LCD | Basel
Buzzer | Mahmoud Sarhan | completed | 0.5 | 0.5
Temperature Sensor | arafa
Timer Manager | Hejazy
APP | Mahmoud Sarhan | completed | 1 | 1
Design Document | Mahmoud Sarhan | compeleted | 4 | 4
header files | Mahmoud Sarhan | compeleted | 1 | 1